## EXAMPLE - Agile Project Plan
AGILE PROJECT PLAN
| PROJECT NAME | Banking Application |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
| PROJECT MANAGER | Talha Iqbal |  |  | 2024-03-14 | 2024-12-31 | 20% | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
No | SPRINT 1 |  | Talha Iqbal. |  | 2024-03-14 | 2024-03-31 | 18
No | User Mangement |  | Nawal Bint Masood. | 3 | 2024-03-14 | 2024-03-22 | 9 | Complete
No | Implement backend logic to save new accounts to the database |  | Mahesh Rani. | 1 | 2024-03-24 | 2024-03-25 | 2 | Complete
No | Add functionality to close user accounts with appropriate confirmation prompts |  | Talha Iqbal. | 2 | 2024-03-28 | 2024-03-29 | 2 | Complete
No | Implement form validation for updating account information |  | Ekjot. | 2 | 2024-03-25 | 2024-03-28 | 4 | Complete
No | Design user interfaces for editing account details. |  | Talha iqbal. | 2 | 2024-03-26 | 2024-03-31 | 6 | Complete
No | SPRINT 2 |  | Talha Iqbal. |  | 2024-04-01 | 2024-04-21 | 21
No | Ensure consistency and usability across account management screens |  | Mahesh Rani. | 2 | 2024-04-01 | 2024-04-06 | 6 | Complete
No | Create wireframes/mockups for account creation, editing, and closing pages |  | Talha Iqbal. | 3 | 2024-04-06 | 2024-04-21 | 16 | In Progress
No | Design UI elements such as forms, buttons, and navigation menus |  | Nawal Bint Masood. | 2 | 2024-04-06 | 2024-04-10 | 5 | In Progress
No | Configure ORM to communicate with database |  | Ekjot. | 2 | 2024-04-12 | 2024-04-15 | 4 | Not Started
No | Create entity models for database tables |  | Ekjot. | 1 | 2024-04-07 | 2024-04-12 | 6 | Not Started
No | SPRINT 3 |  | Talha Iqbal. |  | 2024-04-25 | 2024-05-10 | 16
No | Verify user authenticity from third party |  | Mahesh Rani. | 2 | 2024-04-25 | 2024-04-30 | 6 | Not Started
No | Verify user legal documents feature |  | Talha Iqbal. | 2 | 2024-04-25 | 2024-04-30 | 6 | Not Started
No | Create cron job to send notification to group |  | Nawal Bint Masood. | 2 | 2024-05-01 | 2024-05-07 | 7 | Not Started
No | In app notification feature. |  | Ekjot. | 2 | 2024-05-07 | 2024-05-10 | 4 | Not Started
Formulas:
START DATE = MIN([START DATE, row below]:G11)
END DATE = MAX([END DATE, row below]:H11)